|  | Orange County Master Aging Plan |
| --- | --- |
| 2020-2021 | MAP Implementation Matrix: Year 4 |

Workgroups:

Outdoor Spaces and Buildings

Transportation

Housing

Social Participation and Inclusion

Civic Engagement and Employment

Community Support and Health Services

Communication and Information

Orange County Master Aging Plan Implementation Matrix: Year 4: 2020/21

Outdoor Spaces & Buildings Workgroup

Objective 1.1: Increase engagement of older adults in planning, monitoring, and maintenance processes.

Objective 1.2: Improve accessibility, availability, convenience, and use of outdoor spaces and buildings.

Objective 1.3: Create and implement county and town development and construction regulations and standards that address senior mobility challenges.

Objective 8.1: Increase the accessibility of information regarding available programs, services, and resources.

Transportation Workgroup

Objective 2.1: Expand availability and improve transportation options for older adults.

Objective 2.2: Improve collaboration among public and private transportation services to overcome barriers to mobility.

Objective 2.3: Increase access to transportation information and travel training.

Objective 8.1: Increase the accessibility of information regarding available programs, services, and resources.

Housing Workgroup

Objective 3.2: Develop new affordable senior housing (rental and ownership, including supported housing).

Objective 3.3: Modify and repair existing housing for safety and accessibility.

Objective 3.4: Educate the public about housing options in later life, emphasizing the importance of accessibility, safety, and maintenance.

Objective 3.5: Activate the community to support and improve quality of life for older adults living in long-term care settings.

Objective 3.6: Support Orange County residents to age in community.

Objective 8.1: Increase the accessibility of information regarding available programs, services, and resources.

Social Participation and Inclusion Workgroup

Objective 4.1: Expand opportunities for educational, intergenerational, and cultural programming.

Objective 5.1: Ensure a welcoming, inclusive, and livable community.

Objective 5.2: Promote social inclusion and community cohesion at the senior centers and other community locations.

Objective 7.1: Increase awareness and use of available health and wellness resources.

Objective 8.1: Increase the accessibility of information regarding available programs, services, and resources.

Civic Engagement & Employment Workgroup

Objective 6.1: Create effective pathways for older adults to secure fairly compensated employment, including traditional, alternative, and entrepreneurial options.

Objective 6.2: Expand opportunities for older adults to gain both job-seeking and on-the-job skills.

Objective 6.3: Promote the value of an experienced workforce to local employers.

Objective 6.4: Expand enriching volunteer opportunities for older adults.

Objective 8.1: Increase the accessibility of information regarding available programs, services, and resources.

Community Support & Health Services Workgroup

Objective 7.2: Expand services to help older adults age in their homes and communities.

Objective 7.3: Improve collaboration between medical providers and OCDOA.

Objective 7.4: Address the problem of food insecurity among older adults.

Objective 7.5: Promote and support the growth of the "Village"/neighborhood model of community support across all of Orange County for individuals aging in their homes.

Objective 7.6: Support planning for and fulfillment of individual goals in all stages at the end of life.

Objective 6.4: Expand enriching volunteer opportunities for older adults.

Objective 5.1: Ensure a welcoming, inclusive, and livable community.

Objective 3.5: Activate the community to support and improve quality of life for older adults living in long-term care settings.

Objective 8.1: Increase the accessibility of information regarding available programs, services, and resources.

Communication and Information: All Workgroup + OCDOA Communication Dept.

Objective 8.1: Increase the accessibility of information regarding available programs, services, and resources

Outdoor Spaces and Buildings Workgroup – Year 4 Priorities

| Indicator | Lead Agency | Q1: Jul – Sep 2020 Activities | Q2: Oct – Dec 2020 Activities | Q3: Jan – Mar 2021 Activities | Q4: Apr – Jun 2021 Activities |
| --- | --- | --- | --- | --- | --- |
| Objective 1.1: Increase engagement of older adults in planning, monitoring, and maintenance processes. |  |  |  |  |  |
| Strategy 1.1.1: Increase channels of communication and collaboration between older adults and planning organizations in Orange County relative to outdoor spaces and buildings. |  |  |  |  |  |
| 1.1.1a. A representative from the Orange County Department on Aging (OCDOA) Advisory Board on Aging is added to the Intergovernmental Parks Workgroup. | OCDOA | Meetings of IGPW on old (need a new Aging Board member as former bd. Member rotated off the Aging Bd.) |  |  |  |
| 1.1.1c. Increased communication from and to nature-related organizations regarding natural areas and other public outdoor spaces is achieved through town Planning and Parks and Recreation Departments. | OCDOA |  |  |  |  |
| Strategy 1.1.2: Provide both traditional and innovative means of monitoring and reporting maintenance issues about the condition of outdoor spaces and public buildings. |  |  |  |  |  |
| 1.1.2c. Training programs on using monitoring and reporting systems are provided at OCDOA. | Orange County Asset Management Service (OCAMS), DEAPR, town Public Works and Parks and Recreation departments, OCDOA |  |  |  |  |
| Strategy 1.1.3: Enhance advocacy efforts by and on behalf of older adults relative to the planning and use of public outdoor spaces and buildings. |  |  |  |  |  |
| 1.1.3b. A volunteer workgroup focused on advocacy for outdoor spaces is formed and facilitated by OCDOA. | Advisory Board on Aging, OCDOA | - Ongoing – trying to identify members |  |  |  |
| Objective 1.2: Improve accessibility, availability, convenience, and use of outdoor spaces and buildings. |  |  |  |  |  |
| Strategy 1.2.1: Increase accessibility and safety of public outdoor spaces and buildings to older adults of all abilities. |  |  |  |  |  |
| 1.2.1b. Use of outdoor spaces by older adults is encouraged through special events organized by and/or for older adults. | Outdoor Spaces Group members; Aging & Wellness; Student Groups/ Interns organized by OCDOA | On hold due to COVID-19 |  |  |  |
| 1.2.1f. Senior center staff members are trained on teaching community members how to use the interactive locator map. | DEAPR, OCDOA, OCAMS | https://gis.orangecountync.gove:8443/TrailsAndParks On hold due to COVID-19 |  |  |  |
| 1.2.1h. Signs/trail markers are added at intersections of longer trails. | DEAPR, OCDOA, OCAMS |  |  |  |  |
| Strategy 1.2.2: Enhance the connectivity and maintenance of sidewalks and greenways to improve usability for older adults of all abilities. |  |  |  |  |  |
| 1.2.2d. Internship opportunities are created with university students to help complete the work. | Town Public Works departments, with support from OCDOA, North Carolina Department of Transportation (NCDOT) | On Hold due to COVID-19 Pandemic |  |  |  |
| Strategy 1.2.4: Increase the availability of small-scale outdoor areas and gathering spaces. |  |  |  |  |  |
| 1.2.4c. Intergenerational outdoor spaces and activity stations are established at the senior centers. | Town Planning Departments, OCAMS, with involvement from DEAPR, Chapel Hill Transit (CHT), Orange Public Transportation (OPT), and OCDOA | On Hold due to COVID-19 Pandemic |  |  |  |
| 1.2.4e. At least one bus stop in each town is converted into a wellness stop/integrated garden. | Town Planning Departments, OCAMS, with involvement from DEAPR, Chapel Hill Transit (CHT), Orange Public Transportation (OPT), and OCDOA | Working with Town of Hillsborough to put up movement posters at bus stops. Signage to be ordered. |  |  |  |

Transportation Workgroup – Year 4 Priorities

| Indicator | Lead Agency | Q1: Jul – Sep 2020 Activities | Q2: Oct – Dec 2020 Activities | Q3: Jan – Mar 2021 Activities | Q4: Apr – Jun 2021 Activities |
| --- | --- | --- | --- | --- | --- |
| Objective 2.1: Expand availability and improve transportation options for older adults. |  |  |  |  |  |
| Strategy 2.1.1: Increase the capacity of the current Volunteer Driver Program. |  |  |  |  |  |
| 2.1.1a. Funding is maintained for the Volunteer Driver Program. | OCDOA, with support from transit partners | Received 2-year renewal of Grant Funding from Durham-Chapel Hill-Carrboro Metropolitan Planning Organization (DCHC MPO) for the “Senior Transportation Expansion, Assessment and Mobility Management Project (STEAMM)”. Award increase from $137K to $167K. |  |  |  |
| 2.1.1b. Increased number of volunteer drivers. | OCDOA | - Current drivers are not driving due to COVID - Drivers remain engaged in VDP thru monthly check ins - Invited drivers to participate in Orange County Transit Plan 2020 Survey and Summit. |  |  |  |
| 2.1.1c. Increased ridership. | OCDOA | Transportation Specialist drove 68 one-way trips. Providing emergency transport with strict adherence of PPE protocol |  |  |  |
| 2.1.1d. Scheduling software is evaluated and purchased. | OCDOA | Working with Code the Dream on Rideshare app. Hired UNC PiAP intern 6hr/week to assist |  |  |  |
| 2.1.1e. Expanded range of services is made available, including weekly errand trips and same day service. | OCDOA | Working with VC 55+ to expand program to include Grocery and Pharmacy deliveries |  |  |  |
| Strategy 2.1.2: Pursue solutions to meet the need for increased transit service hours and access to more destinations. |  |  |  |  |  |
| 2.1.2a. A needs assessment is conducted to define the needs and gaps in service hours and destinations. | CHT, OCPT | Extensive assessment conducted by Orange County Transit Plan 2020 – will be shared in October at Summit |  |  |  |
| 2.1.2b. Service hours and destinations are increased by OPT and EZ Rider. | CHT, OCPT | - Both EZ Rider and OCPT reduced services April and May due to COVID. Both are limiting passenger count and adhering to PPE protocols - Stage 3 coming in October |  |  |  |
| 2.1.2c. Affordable options are created for wheelchair transport to non-medical destinations for residents living outside of Chapel Hill/Carrboro. | CHT, OCPT | - Both EZ Rider and OCPT reduced services April and May due to COVID. Both are limiting passenger count and adhering to PPE protocols |  |  |  |
| 2.1.2d. Same day service to urgent care appointments is established. | CHT, OCPT | - OCDOA pilot of Mobility on Demand Uber/Lyft model program in Hillsborough continues to be developed, but implementation is on hold due to COVID |  |  |  |
| Objective 2.2: Improve collaboration among public and private transportation services to overcome barriers to mobility. |  |  |  |  |  |
| Strategy 2.2.1: Establish a medical transportation work group that meets quarterly with representatives from transit, health, and aging services focused on improving coordination of medical transportation and other issues. |  |  |  |  |  |
| 2.2.1b. Grant opportunities are identified and pursued. | OCDOA | Waiting on results of UNC research team for “First Mile to Using Data Analytics to identify and Address Transport Barriers to Care” to see if the MAP Transportation workgroup will participate in the design and testing of their data platform |  |  |  |
| 2.2.1c. Older adult riders are able to travel from Orange County into neighboring counties for medical appointments and between Chapel Hill/Carrboro and Hillsborough. | OCDOA, OCPT, CHT | - Durham Area Transit Authority and Durham County Access both submitted and received 5310 grant funds for 2020/21. Will try and reinstate - Will initiate conversations to identify transfer points between their services and OCPT & CHT |  |  |  |
| 2.2.1d. Transit dependent patients are identified by healthcare providers and assisted with securing transportation to appointments. | OCDOA, CHT, GoTriangle, OCPT, Duke Health, UNC Healthcare | Will discuss a shared method of identification at next MAP Transportation meeting |  |  |  |
| Strategy 2.2.2: Establish streamlined door-to-door transportation across county lines and between Orange County and Chapel Hill/Carrboro. |  |  |  |  |  |
| 2.2.2a. Older adult riders are able to travel from Orange County into neighboring counties and between Chapel Hill/Carrboro and Hillsborough. | CHT, OCPT OCDOA | (see 2.2.1c) |  |  |  |
| 2.2.2b. Options are explored for simplifying the reservation process for a two-part ride. | CHT, OCPT OCDOA | (see 2.2.1c) |  |  |  |
| Strategy 2.2.3: Educate transit dependent older adults about emergency/disaster preparedness and planning. |  |  |  |  |  |
| 2.2.3a. Education about notification processes and options for assistance in times of emergency is provided to transit dependent older adults. | OCDOA | Looking into information provided on the EMS Emergency Preparedness Checklist |  |  |  |
| 2.2.3b. Volunteer Driver program recipients are assisted in making plans for emergency preparedness. | OCDOA | VDP riders are asked about their emergency plans when they enroll in the program. |  |  |  |
| Objective 2.3: Increase access to transportation information and travel training. |  |  |  |  |  |
| Strategy 2.3.1: Educate older adults to access transit information. |  |  |  |  |  |
| 2.3.1a. Education is provided regarding information available on transportation websites relevant to county and town services. | OCDOA, CHT, OCPT, GoTriangle | - Transportation information and resources are available M-W-F via the Senior Nutrition program at Seymour Senior Center - Transportation information and resources are available every 3rd T-TH via the CSFP Food box program at both Senior Centers, and Cedar Grove Community Center |  |  |  |
| 2.3.1b. Easy to read user guides are published and regularly updated. | OCDOA, CHT, OCPT, GoTriangle | - Ongoing distribution of newly revised and easy to read transportation pamphlet |  |  |  |
| 2.3.1c. Distribution locations for transportation information are identified and supplied with updated information. | OCDOA, with support from OPT, CHT, community centers and public libraries | - Transportation tabling and presentations have been placed on hold due to COVID - Presenter for “Driving; Planning for Retirement” through the Caregiver Summit being offered in October. Free to all. Over 1000 registered |  |  |  |
| 2.3.1d. Regularly scheduled classes on subjects such as Bus Riding 101, Uber/Lyft, and Transit Apps for smartphone users are held at Senior Centers, libraries and community centers, senior apartment complexes. | OCDOA | - Bus Riding 101 class has been placed on hold due to COVID - Provided individual training sessions to residents who contacted Aging Helpline or Transportation Helpline |  |  |  |
| 2.3.1e. Transportation Help Line and Go Triangle Call Center phone numbers are widely distributed. | OCDOA, GoTriangle |  |  |  |  |
| Strategy 2.3.2: Improve door-to-door and fixed route services to increase comfort and confidence of older adult riders. |  |  |  |  |  |
| 2.3.2a. Universal symbols are used on all public buses, signs, and literature in Orange County to overcome language barriers and low literacy. | OPT, CHT, OCDOA | - Will discuss how universal symbols are used on all public buses, signs, and literature in Orange County at next MAP Transportation meeting |  |  |  |
| 2.3.2b. Riders of door-to-door services are given real time information about bus arrival time and new technology for call back response system is employed. | OPT, CHT | - Will discuss real time methods of sharing ridership information at next MAP Transportation meeting |  |  |  |
| 2.3.2c. Travel training for new bus riders is offered on a regular basis. | OPT, CHT, OCDOA | - Still exploring ways to resume travel training during COVID |  |  |  |
| Objective 5.2: Promote social inclusion and community cohesion at the senior centers and other community locations. |  |  |  |  |  |
| Strategy 5.2.1: Increase awareness of transportation options so that people are better able to access events and services. |  |  |  |  |  |
| 5.2.1a. Transportation Specialist is listed as a resource on publications for events. | OCDOA | - Most social events happening virtually due to COVID - Transportation Specialist contact information is listed under relevant events in Senior Times. |  |  |  |
| 5.2.1b. A ride sharing board is created to organize carpooling to special events, especially in the evenings. | OCDOA | - Most social events happening virtually due to COVID - Will revisit working with Social and Communications Workgroups |  |  |  |

Housing Workgroup – Year 4 Priorities

| Indicator | Lead Agency | Q1: Jul – Sep 2020 Activities | Q2: Oct – Dec 2020 Activities | Q3: Jan – Mar 2021 Activities | Q4: Apr – Jun 2021 Activities |
| --- | --- | --- | --- | --- | --- |
| Objective 3.1: Modify, eliminate, or create policies that result in full realization of the MAP housing goal. |  |  |  |  |  |
| Strategy 3.1.1: Create an inter-governmental Senior Housing Workgroup to study and recommend changes to relevant local and state housing policies, especially during times of key policy reviews. |  |  |  |  |  |
| 3.1.1a. A Housing Task Force is developed. |  | - Housing Workgroup members continued participation in Affordable Housing Coalition. - New intern to support Coalition activities was hired for Oct. 5 start. Coalition members supported funding for intern. Administration of internship via UNC Partnerships in Aging Program. |  |  |  |
| 3.1.1b. A list of state and local polices to target is created and changes are recommended. |  | COMPLETED |  |  |  |
| Objective 3.2: Develop new affordable senior housing (rental and ownership, including supported housing). |  |  |  |  |  |
| Strategy 3.2.1: Advocate for incentives and financing that encourages affordable and age- friendly housing development, both conventional and innovative. |  |  |  |  |  |
| 3.2.1a. Additional public-private partnerships are developed to increase affordable housing options for older adults. | OCDOA/ Advisory Board/ UNC Partnerships in Aging Program (PiAP) | - Carrboro’s affordable housing special revenue fund, expecting to support Cobb Street Habitat property - Casa project on Merritt Mill road, Carr/CH border- received state funding through low income tax program, moving forward, planning on breaking ground in the spring - PeeWee Home on Mitchell Lane in permitting phase. Expected to break ground in November. |  |  |  |
| 3.2.1b. Support is provided for senior housing proposals for County Bond funding, if appropriate. |  | None |  |  |  |
| 3.2.1c. A pilot project focused on shared, supportive housing models is created. | OCDOA/ Advisory Board, OC Housing Dept, UNC Partnerships in Aging Program | Eldercare Power Team begun in Northside neighborhood. Bi-weekly review of individual elders for support and services, including housing. |  |  |  |
| 3.2.1d. One site for development of age-friendly housing is identified in each of the Orange County jurisdictions: Carrboro, Chapel Hill, Hillsborough, and the county. | OCDOA, OC Housing Dept | COMPLETED | COMPLETED | COMPLETED | COMPLETED |
| 3.2.1e. Tax incentives are created that encourage accessible housing design and repair. |  | Currently approaching through a racial equity lens. OCHPC has sent specific policy questions, much related to tax policy, regarding home repair and preservation to the towns and the county for incorporation into their respective GARE processes. |  |  |  |
| 3.2.1f. OCDOA is consulted with by developers and financers at the conceptual stage to ensure home and neighborhood designs are age-friendly. | OCDOA/ UNC Partnerships in Aging Program (PiAP) | No new consultations |  |  |  |
| 3.2.1g. The number of units built that are targeted to older adults is increased by at least 20%. | OCDOA | GOAL exceeded (37% on the books but developments have been delayed due to COVID) |  |  |  |
| 3.2.1h. The number of age-friendly units built within larger mixed income developments is increased. | OCDOA | - 2200 Homestead Road, 120 units by Community Home Trust, Casa, Self-Help. Mixed use housing. Public meetings starting this fall for the next 6 months - Weavers Grove, Habitat Development of 100units. Planning on breaking ground in the spring |  |  |  |
| Objective 3.3: Modify and repair existing housing for safety and accessibility. |  |  |  |  |  |
| Strategy 3.3.1: Increase and expedite repairs and modifications of existing housing. |  |  |  |  |  |
| 3.3.1a. The public bidding process for the County Urgent Repair Program is replaced with a newly created and vetted list of approved contractors. | OC Housing | COMPLETED |  |  |  |
| 3.3.1b. New pathways for project permitting are developed through collaboration by regulatory organizations. | OC Planning, OC Housing Departments | Reached out to OC Planning and was given the names of two specialists that older adults could call with questions. |  |  |  |
| 3.3.1c. Jobs are completed faster for clients in the Urgent Home Repair Program. |  | Ongoing assessment of this goal through OCHPC program evaluation. |  |  |  |
| 3.3.1d. Wait times are decreased for residents needing urgent home repairs. | OC Housing, OC Planning, OCDOA | Ongoing assessment of this goal through OCHPC program evaluation. |  |  |  |
| 3.3.1e. Number of accessibility repairs performed is increased. | OC Housing, OCDOA | Closed as no longer appropriate. |  |  |  |
| 3.3.1f. Skilled workers who can provide home repair/remodels for community members are identified by Local Fire Districts. |  | Not feasible. Handy Helpers program is alternative. |  |  |  |
| 3.3.1g. Managers of existing senior housing developments consult with OCDOA about accessible repairs and modifications. | OCDOA | None |  |  |  |
| Objective 3.4: Educate the public about housing options in later life, emphasizing the importance of accessibility, safety, and maintenance. |  |  |  |  |  |
| Strategy 3.4.1: Offer community events and educational materials to assist residents and family members in planning for their housing needs in later life. |  |  |  |  |  |
| 3.4.1a. Aging in Community series is continued to educate the public about age-friendly housing models, especially “missing middle” housing (i.e., duplexes and small scale apartments with courtyards). | OCDOA | No events planned at this time. |  |  |  |
| 3.4.1b. Aging Readiness Campaign is created with yard signs, interactive websites, and resources that can help older adults and family members plan for their future housing needs. | OCDOA/ UNC Partnerships in Aging Program (PiAP) | UNC PiAP intern continued position with OCDOA to advance aging readiness through social media. |  |  |  |
| 3.4.1c. Residents are educated on how to prevent future need for repairs and modifications, and connected to appropriate organizations and services. |  | OCHPC has launched Phase 1 of Education modules in partnership with the MCJC, Habitat, and Hope Renovations. Phase 2 (4 in-depth workshops) is in planning phase for Spring 2021. |  |  |  |
| Strategy 3.4.2: Create opportunities to improve relationships between residents, inspectors, and planning officials. |  |  |  |  |  |
| 3.4.2a. Orange County Planning Department website is updated to include frequently asked questions. | OC Planning Department | Not feasible. Planning department provided specialists to call instead. |  |  |  |
| 3.4.2b. Programs are developed to make information about inspections available and decrease misconceptions. |  | No feasible. Planning department provided specialists to call instead. |  |  |  |
| 3.4.2c. Programs are developed to decrease misconceptions about partial repairs. |  | Not feasible. Planning department provided specialists to call instead. |  |  |  |
| Objective 3.6: Support Orange County residents to age in community. |  |  |  |  |  |
| Strategy 3.6.1: Create and fund a new OCDOA housing specialist position to educate, activate, and coordinate the community in achieving MAP housing goals. |  |  |  |  |  |
| 3.6.1a. Position is created and filled with support from housing agency partners. | OC Housing Department, OCDOA | OC Department of Housing and Community Development has 3 new hires to support emergency housing assistance and support allocation of CARES funds. Members of this Department have joined the MAP workgroup. |  |  |  |
| 3.6.1b. Older adults are connected to and supported to live in housing options of their choice. |  | OCDOA collecting data about frequency of housing related calls to Aging Helpline. Exploring support for virtual shared housing bulletin board. |  |  |  |
| Strategy 3.6.2: Collaborate across repair/remodel organizations to better communicate, share cases, and refer to specialized services. |  |  |  |  |  |
| 3.6.2a. Network of repair/remodel organizations is developed. |  | COMPLETED (OCHPC ongoing work) |  |  |  |
| 3.6.2b. Collaboration coordinator is selected. |  | Current temporary position term ends in May 2021. Renewed attention to sustainability of this goal. |  |  |  |
| 3.6.2c. Representative from each organization is designated to network. |  | COMPLETED (OCHPC ongoing work) |  |  |  |
| 3.6.2d. Referrals are increased across organizations. |  | Ongoing assessment through OCHPC Program evaluation which is supported through a UNC PiAP intern working with Handy Helpers |  |  |  |
| 3.6.2e. Multiple repairs are provided by multiple organizations through use of coordinated repair network. |  | (see 3.6.2d.) |  |  |  |
| 3.6.2f. More comprehensive repairs are provided to residents. |  | (see 3.6.2d.) |  |  |  |
| 3.6.2g. Data are collected and shared regarding safety and well-being of residents who receive home repairs or modifications. |  | (see 3.6.2d.) |  |  |  |
| 3.6.2h. Funding is increased for repairs and remodels that partially, but not entirely, bring a home up to code. |  | CARES funding has provided additional funds for ramps through Handy Helpers. |  |  |  |
| 3.6.2i. Training is developed for OCDOA employees and others who make home visits regarding home safety resources and services. |  | This is no longer applicable or needed given the development of the OCHPC’s processes. Close. |  |  |  |

Social Participation and Inclusion Workgroup – Year 4 Priorities

| Indicator | Lead Agency | Q1: Jul – Sep 2020 Activities | Q2: Oct – Dec 2020 Activities | Q3: Jan – Mar 2021 Activities | Q4: Apr – Jun 2021 Activities |
| --- | --- | --- | --- | --- | --- |
| Objective 4.1: Expand opportunities for educational, intergenerational, and cultural programming. |  |  |  |  |  |  |
| Strategy 4.1.1: Ensure that programming is accessible, sensitive, and inclusive to people based on a broad variety of needs and abilities. |  |  |  |  |  |  |
| 4.1.1a. Assistive technologies (e.g., listening devices, large text or audio, mobility assistance, etc.) are made available for people who need it. | OCDOA | Ongoing. Some written and some person-to-person assistance provided with virtual programming. |  |  |  |
| 4.1.1b. Programming is made available in multiple languages, in partnership with community groups. | OCDOA | Ongoing but very limited during this quarter due to COVID-19 current staffing limitations during this time. |  |  |  |
| 4.1.1c. Consultation is sought out from organizations like North Carolina Assistive Technologies, North Carolina Division of Deaf and Hard of Hearing, North Carolina Division of Services for the Blind, and Club Nova. | OCDOA | Ongoing – on hold due to COVID-19 |  |  |  |
| 4.1.1d. Programming is attended by older adults from diverse populations (e.g., minority, LGBTQ, refugee, faith communities, and people with physical, mental, cognitive, and/or intellectual disabilities). | OCDOA | Ongoing – limited due to COVID-19 |  |  |  |
| Strategy 4.1.2: Expand space availability for social/educational programming to meet anticipated growth of older adult population. |  |  |  |  |  |  |
| 4.1.2a. Senior centers are expanded to include more space for recreational activities, kitchen/cooking space, theater space, common space that encourages groups to intermingle, health services space, exercise rooms, and storage space. | OCDOA | Seymour Construction has continued throughout the first quarter and is nearing completion. |  |  |  |
| 4.1.2b. Additional programming for older adults is made available within the senior centers and in other settings. | OCDOA | - Virtual and new “parking lot” programs created and available due to COVID-19, Virtual Offerings posted on website and social media, and shared with County Community Relations Director for promotion: 5 – Art 14 – Crafts 8 – Dance, Music, Theater 18 – Educational 4 – Language 4 – Pottery classes 34 – Computer classes 35 – Special Events 16 – Wellness Special Events 10 – Exercise Classes - Note: The congregate meal program has never ceased due to COVID-19; it changed to curbside - 3 days per week w/ 2 meals per day! |  |  |  |
| 4.1.2c. More people participate at the senior centers. | OCDOA | Participation is down compared to 1 year ago and time before COVID-19 related to Stay at Home orders and guidance |  |  |  |
| Strategy 4.1.3: Create more opportunities for intergenerational programming. |  |  |  |  |  |  |
| 4.1.3a. One intentional intergenerational program per year is created and evaluated, which encourages older adults and younger people to work with each other (e.g., Prime Time Players works with high school drama department to put on show, co-sponsored community service project). | OCDOA | Story Time Adventure with Law Enforcement is planned to be offered on 11/7 |  |  |  |
| 4.1.3b. Partnerships are created with other agencies for intergenerational opportunities (e.g., schools, daycare centers, colleges/universities, scout troops, faith communities, fraternities and sororities, YMCA, local businesses, etc.). |  | Ongoing but on hold due to COVID-19 |  |  |  |
| 4.1.3c. More young people are involved in senior center programming. |  | Ongoing but on hold due to COVID-19 |  |  |  |
| Strategy 4.1.4: Expand awareness and availability of scholarships/fee reductions. |  |  |  |  |  |  |
| 4.1.4a. Awareness of availability of scholarships/fee reductions is increased. | OCDOA | Ongoing |  |  |  |
| 4.1.4b. More scholarships/fee reductions are utilized for programming. | OCDOA | On hold due to COVID-19 |  |  |  |
| 4.1.4c. Increased demand for scholarships/fee reductions is met, as needed, through additional sponsors. | OCDOA | On hold due to COVID-19 |  |  |  |
| 4.1.4d. Assistance is provided to participants who need help filling out a scholarship/fee reductions form. | OCDOA | Ongoing as requested |  |  |  |
| Strategy 4.1.5: Create a “Senior Center Without Walls” project for older adults who are unable to leave their homes but want to participate in senior center activities. |  |  |  |  |  |  |
| 4.1.5a. A pilot of the program is created, launched, and evaluated. | OCDOA | - Due to the COVID-19 pandemic, virtual programming has been increased substantially. - There is currently outreach efforts made to ID those who are in isolation and may welcome some computer or virtual access - OCDOA Leadership participating on a statewide plan to look at Social isolation |  |  |  |
| 4.1.5c. Volunteers are recruited to manage cameras, edit, work on AV, etc. | OCDOA | - On hold due to COVID-19 |  |  |  |
| 4.1.5e. A library of DVDs with programming is available for check out. | OCDOA | - A library of In Praise of Age tapes is filed and listed on OCDOA files. List available upon request. - An OCDOA YouTube Channel has been developed and available on OCDOA Website. 32 views during August and Sept |  |  |  |
| 4.1.5f. The number of views and DVD checkouts increases as the program continues. | OCDOA |  |  |  |  |
| Objective 5.1: Ensure a welcoming, inclusive, and livable community. |  |  |  |  |  |  |
| Strategy 5.1.1: Ensure that all programs and services provided through OCDOA are based on cultural humility and inclusivity. |  |  |  |  |  |  |
| 5.1.1a. Sensitivity and inclusivity training is provided to OCDOA staff once per year. | OCDOA | On hold due to COVID-19 |  |  |  |
| 5.1.1b. Signage at OCDOA is welcoming and inclusive to all. | OCDOA | On hold due to COVID-19 |  |  |  |
| 5.1.1c. Clientele is surveyed to learn what languages would be most important to include on signs and forms. Signs and forms are adjusted to reflect that data. | OCDOA | On hold due to COVID-19 |  |  |  |
| 5.1.1d. Senior centers are attended by older adults from diverse groups. | OCDOA | Ongoing, but on hold due to COVID-19 “Stay at Home” orders |  |  |  |
| 5.1.1e. OCDOA works with organizations and individuals who advocate for diverse populations and barriers are identified and overcome. | OCDOA | Ongoing |  |  |  |
| Strategy 5.1.2: Continue and expand outreach to growing refugee and immigrant populations to build interest in services and presence at senior centers. |  |  |  |  |  |  |
| 5.1.2a. Awareness about OCDOA services is increased and information is shared with pertinent organizations (e.g., church refugee initiatives; churches that provide services in other languages; Refugee Wellness Center; Refugee Support Center; Refugee Community Partnership; Refugee Resettlement Agencies; Spanish Social Club; El Centro Hispano; apartment complexes/retirement communities). | OCDOA | Ongoing, but limited due to COVID-19 |  |  |  |
| 5.1.2b. OCDOA staff work with these groups to find out what services and programming they are most interested in, and those services are provided. |  | Ongoing, but limited due to COVID-19 |  |  |  |
| 5.1.2c. Activities and information are offered in relevant languages. | OCDOA | Ongoing, but limited due to COVID-19 |  |  |  |
| 5.1.2d. Number of individuals from identified groups who attend the Senior Center programming and utilize services increase. | OCDOA | Limited due to COVID-19 “Stay at Home” order |  |  |  |
| Strategy 5.1.4: Improve accessibility within the senior centers. |  |  |  |  |  |  |
| 5.1.4a. OCDOA staff is trained on accessibility issues and resources. | OCDOA | On hold due to COVID-19 |  |  |  |
| 5.1.4c. OCDOA staff work with groups who are navigating the senior centers to learn what is problematic. |  | On hold due to COVID-19 |  |  |  |
| 5.1.4d. Participants and family members are aware of what kind of equipment is available at the centers to improve accessibility, where it is located, and how to use it. | OCDOA | Ongoing but limited due to COVID-19 |  |  |  |
| Objective 5.2: Promote social inclusion and community cohesion at the senior centers and other community locations. |  |  |  |  |  |  |
| Strategy 5.2.1: Increase awareness of transportation options so that people are better able to access events and services. |  |  |  |  |  |  |
| 5.2.1a. Transportation Specialist is listed as a resource on publications for events. | OCDOA, Cardinal Innovations | Ongoing (cross listed with Transportation Workgroup) |  |  |  |
| Strategy 5.2.2: Provide and encourage social connections between older adults. |  |  |  |  |  |  |
| 5.2.2a. More social groups are developed. | OCDOA, Cardinal Innovations | Ongoing, with limits due to COVID-19 |  |  |  |
| 5.2.2b. More opportunities for one-on-one activities are made available. | OCDOA | Ongoing, with limits due to COVID-19 |  |  |  |
| 5.2.2c. People come to the senior centers to socialize. | OCDOA, Cardinal Innovations | Suspended due to COVID-19 |  |  |  |
| 5.2.2d. More older adults are served at the senior centers, as measured through increased attendance, participation, and demand. | OCDOA | Suspended due to COVID-19 |  |  |  |
| 5.2.2f. A “Meet Your Neighbor” or “Bring A Friend” day is held quarterly, during which members are encouraged to bring others to the senior center. | OCDOA | Ongoing, but suspended due to COVID-19 |  |  |  |

Civic Participation and Employment Workgroup – Year 4 Priorities

| Indicator | Lead Agency | Q1: Jul – Sep 2020 Activities | Q2: Oct – Dec 2020 Activities | Q3: Jan – Mar 2021 Activities | Q4: Apr – Jun 2021 Activities |
| --- | --- | --- | --- | --- | --- |
| Objective 6.1: Create effective pathways for older adults to secure fairly compensated employment, including traditional, alternative, and entrepreneurial options. |  |  |  |  |  |
| Strategy 6.1.1: Create an Older Adult Employment Collaborative that is actively involved in creating and supporting employment opportunities for older workers. Partners should include: OCDOA, Orange County Department of Social Services (DSS), Orange County Economic Development, AARP, Chapel Hill and Hillsborough Chambers of Commerce, and Durham Technical Community College (Durham Tech), National Caucus and Center on Black Aging, Inc. |  |  |  |  |  |
| 6.1.1c. Employment pathways are identified or created, and disseminated through a centralized location. | OCDOA | Continuing to search for additional links and virtual meetings. Added Colonial Job Seekers and St. Michael’s networking groups to list on Mature Job Seeker’s web site and noted in Endless Possibilities newsletters. |  |  |  |
| 6.1.1d. Interested older adults secure meaningful, fairly compensated employment, including traditional, alternative, and entrepreneurial options. | Older Adult Employment Collaborative | Employment Specialist helped mature job seekers (find event details below): - July – 46 (23 individual contacts and 23 at events) - Aug – 69 (28 individual contacts and 41 at events) - Sept – (61 – 28 individual contacts, 33 at events) |  |  |  |
| Strategy 6.1.2: Promote alternative and entrepreneurial employment opportunities for older adults. |  |  |  |  |  |
| 6.1.2a. Classes are provided to older adults at senior centers and public libraries to explore entrepreneurial employment opportunities. | Older Adult Employment Collaborative, in partnership with the Orange County Public Library | Hosting events virtually as in person events on hold due to COVId-19 pandemic, will revisit |  |  |  |
| 6.1.2c. Alternative and entrepreneurial job seeking older adults report securing or connecting with desired job opportunities. | Older Adult Employment Collaborative, in partnership with the Orange County Public Library | On hold during COVID-19 pandemic |  |  |  |
| Strategy 6.1.3: Host a job fair and networking event to connect older adults with interested employers. |  |  |  |  |  |
| 6.1.3a. Seminars for older adult job seekers are held to prepare them for successful networking at event. | OCDOA, in collaboration with DSS, AARP, and Chapel Hill and Hillsborough Chambers of Commerce | - Employment Specialist collaborated on TAFU (To Avoid Future Unemployment) virtual meetings on July 9, July 23, Aug 6, Aug 20 - “Being Better than Before” Webinar Series on July 1, Sept 23, Sept 25, Sept 30, Oct 2 |  |  |  |
| 6.1.3b. Job fair and networking events are held, with transportation options. | OCDOA, in collaboration with DSS, AARP, and Chapel Hill and Hillsborough Chambers of Commerce | - Employment Specialist facilitated Jobs Network virtual meeting on July 11, July 25, Aug 8, Aug 22 - NC Biotechnology Center Networking meeting on July 13, Aug 17, Aug 31 Colonial Baptist Job Seekers meetings on Aug 3, 10, 17, 24, 31 |  |  |  |
| Strategy 6.1.4: Create “Senior Internship” opportunities, whereby older adults obtain internships with possibility of future hire. |  |  |  |  |  |
| 6.1.4a. Research is conducted and recommendations are created about best practices for a “Senior Internship”. | Older Adult Employment Collaborative | On hold during COVID-19 pandemic |  |  |  |
| 6.1.4b. “Senior internships” are created with partners in the county. |  | On hold during COVID-19 pandemic |  |  |  |
| Objective 6.2: Expand opportunities for older adults to gain both job-seeking and on-the-job skills. |  |  |  |  |  |
| - Strategy 6.2.1: Expand existing and create additional resources for older adults seeking employment. |  |  |  |  |  |
| 6.2.1a. An inventory of what services already exist in the county is created and research on best practices is conducted. | Older Adult Employment Collaborative, with support from Orange County Public Library | - Continue to update Mature Job Seekers Guide (https://www.orangecountync.gov/DocumentCenter/View/5128/OCDOA-Mature-Job-Seekers-Resource-Guide-FINAL?bidId=) - Continue to offer employment services offered by OCDOA. For example, in addition to holding events, Employment Specialist is available by appointment to help individuals with processes like job identification, applications, resumes, networking, interviewing, and more |  |  |  |
| 6.2.1b. More older adults report utilizing and benefiting from these resources and services. | Older Adult Employment Collaborative, with support from Orange County Public Library | Tracking and reporting (see 6.1.1d.) |  |  |  |
| 6.2.1c. Resources and services are offered in Orange County locations in addition to Durham Tech. | Older Adult Employment Collaborative, with support from Orange County Public Library | Posting services on LinkedIn, Facebook, Twitter; add Library when they open to public |  |  |  |
| 6.2.1d. New training opportunities are held and evaluated. | Older Adult Employment Collaborative, with support from Orange County Public Library | - See events under 6.1.3 - Employment Specialists began planning regular virtual presentations with office hours |  |  |  |
| Objective 6.3: Promote the value of an experienced workforce to local employers. |  |  |  |  |  |
| Strategy 6.3.1: Create awareness campaign designed to (1) promote older adults as productive, experienced, reliable, and entrepreneurial members that positively impact the labor force; (2) highlight employers that are successfully integrating older adult workers; and (3) provide information to Orange County employers to best serve an older adult workforce. |  |  |  |  |  |
| 6.3.1a. Research is conducted to better understand barriers and facilitators to employing older adults. | AARP, in collaboration with OCDOA, Chapel Hill and Hillsborough Chambers of Commerce, and Orange County Economic Development | When hiring environment improves, initiate discussion with business owners to determine if practical to pursue, and when. |  |  |  |

Community Support and Health Services Workgroup – Year 4 Priorities

| Indicator | Lead Agency | Q1: Jul – Sep 2020 Activities | Q2: Oct – Dec 2020 Activities | Q3: Jan – Mar 2021 Activities | Q4: Apr – Jun 2021 Activities |
| --- | --- | --- | --- | --- | --- |
| Objective 7.1: Increase awareness and use of available health and wellness resources. |  |  |  |  |  |
| Strategy 7.1.1: Offer and promote health and wellness programs in the senior centers, and throughout the community, for older adults of all abilities. |  |  |  |  |  |
| 7.1.1a. Health and wellness programs, including evidence-based programs, are offered in senior centers and throughout the community (including in rural locations). | OCDOA, with support from DEAPR, UNC Health Care, Towns of Carrboro, Chapel Hill, and Hillsborough, and the Orange County SportsPlex | - Many physical activity programs transitioned to virtual offerings (FB and Zoom). - Increased the number of mental health classes and programs to match needs during COVID - Partnering for UNC Health Care for 1:1 hearing screenings - Partnering with Walgreens to offer flu shots - Health Department offering diabetes self-management education and nutrition counseling services as well as fun/rec classes (e.g., “stay well bingo”). - Nurses needed for OCDOA Fit Feet program. - Hosting multiple virtual programs for falls prevention awareness week in Sept - OCDOA OT completed a virtual home safety tour - UNC Health Care has been focusing on COVID response. They recently applied for a grant to expand community-wide testing capacity, especially in rural communities. |  |  |  |
| 7.1.1d. Seymour Center fitness studio is expanded and redesigned to increase capacity and update technology. | OCDOA, with support from DEAPR, UNC Health Care, Towns of Carrboro, Chapel Hill, and Hillsborough, and the Orange County SportsPlex | - Fitness room has been moved |  |  |  |
| 7.1.1e. More older adult opportunities are offered in SportsPlex Fieldhouse expansion. | OCDOA, with support from DEAPR, UNC Health Care, Towns of Carrboro, Chapel Hill, and Hillsborough, and the Orange County SportsPlex | - Currently no programing due to COVID 19 |  |  |  |
| Strategy 7.1.2: Provide behavioral health support and programming to older adults and their caregivers. |  |  |  |  |  |
| 7.1.2a. More support groups are provided (e.g., health, grief, depression, life transitions, substance abuse, etc.) in various locations. | OCDOA, in partnership with Cardinal Innovations Healthcare, NAMI, UNC Health Care, Duke Home Care and Hospice, Grief Oasis (CH) | - Maintaining caregiver support groups virtually. - Starting new support group for those experiencing mental health challenges such as anxiety depression (especially during COVID), led by LCSW-A - PACE offering virtual grief support group with chaplain. |  |  |  |
| 7.1.2b. Directory of mental health therapists and support groups appropriate for older adults is created and updated. | OCDOA, in partnership with Cardinal Innovations Healthcare, NAMI, UNC Health Care | - SRT completed this. Can feed into NC CARES 360 |  |  |  |
| 7.1.2c. Mental health (e.g., Mental Health First Aid) training is provided at least twice per year at senior centers, public libraries, and long-term care facilities. | OCDOA, in partnership with Cardinal Innovations Healthcare, NAMI, UNC Health Care | - Cardinal is offering virtual trainings for: 1. Older Adult Mental Health First Aid and 2. Question, Persuade, Refer (QPR) suicide prevention. EMS is interested in these trainings. Contact information shared. |  |  |  |
| 7.1.2d. Behavioral Health informational workshops are provided at both senior centers at least annually. | OCDOA, in partnership with Cardinal Innovations Healthcare, NAMI, UNC Health Care | - OCDOA Mental Wellness SRT hosted a virtual event, “Let’s Talk about Mental Health During COVID”, on July 23 |  |  |  |
| Objective 7.2: Expand services to help older adults age in their homes and communities. |  |  |  |  |  |
| Strategy 7.2.1: Expand community-based health and support programs that support older adults’ health and safety. |  |  |  |  |  |
| 7.2.1a. The capacity of the OCDOA Aging Transitions program is expanded to help more older adult residents “age in place”. | OCDOA | - Able to do 1:1 visits for folks who can get to center and starting driveway visits this fall with existing and new clients - OCDOA already has a durable medical equipment loaning program for smaller items such as walkers. They are currently working on a database for larger pieces such as lifts and beds. - OCDOA have increased efforts to address social isolation during COVID (see Social Participation for additional details) - Aging Transitions MSW interns began calling and assessing nearly 1600 registered members of senior center who have not participated in programs since beginning of COVID - UNC Hillsborough Hospital leading multiple efforts to adapt health services to better serve seniors in our community: 1. NC’s First Geriatrics Accredited ED, 2. member of the age friendly hospital network, 3. staff completed all training and now considered to be a dementia friendly hospital, and 4. new Geriatric Fellows will be shadowing EMS Strike Team. |  |  |  |
| 7.2.1b. EMS/OCDOA Stay Up and Active Program is expanded, allowing more people to access follow-up services after a fall is reported and expanding capacity to provide fall risk. | EMS/OCDOA | - Was paused due to COVID, meeting scheduled in Sept to regroup. - EMS saw a reduction in falls at the start of COVID (32 fewer compared to last year, since 2018 looking at March – Jun 2020 has 122 fewer falls), numbers are now increasing - EMS has been partnering with PACE to decrease unnecessary ED visits - Piedmont Health has noticed a slight increase in falls since the start of COVID |  |  |  |
| 7.2.1d. “Remembering When” home inspections to correct fire-related concerns (e.g., batteries, smoke/CO2 detectors, minor electrical/lighting, dryer venting) are conducted. | OC Emergency Services | - On hold |  |  |  |
| 7.2.1e. Educational programs are provided at the senior centers yearly to increase awareness and use of technology for home safety. | OCDOA/Senior Centers | - Working with IG SRT to help with technology training classes, Partnering with CH/Carr city schools and UNC school of Pharm, ProjectAGE project will help with technology assistance - Home safety virtual 2x month Safety Chat to help keep people safe - Seymour Tech moved to all virtual classes – 34 classes in recent issue - Kramden Institute (nonprofit in Durham) provides classes and computers |  |  |  |
| Strategy 7.2.2: Identify and expand service areas that volunteers can assist with or create to reduce cost and expand availability. |  |  |  |  |  |
| 7.2.2a. A resource pool of retired nurses and doctors is created that can help older adults successfully use the healthcare system for prevention and curative services. | OCDOA / VC55+ | - Plans to launch pilot health navigator program in the spring. Materials are prepared and ready to launch when conditions are safer (on hold during COVID due to in-person 1:1 interactions) |  |  |  |
| 7.2.2b. A health coordination pilot program is established between UNC Hospital-Hillsborough and at least one faith-community. | OCDOA, UNC Health Care | - OCDOA, Faith Outreach SRT, and UNC Health Care hosted virtual Faith Outreach Qrtly Breakfast focused on Social Isolation on Sept 14 - UNC Capstone team project on hold. |  |  |  |
| 7.2.2c. Volunteers are recruited and supported to help older adults manage instrumental tasks of daily living (e.g., mail processing, check writing, bookkeeping, etc.). | OCDOA / VC55+ | - (see 7.2.2a) Mail Management program is also ready to go but on hold during COVID. Hoping to launch in winter or spring. |  |  |  |
| 7.2.2d. Policies at OCDOA are reviewed to make it easier for volunteers and concerned citizens to refer at-risk individuals to the OCDOA for services. | OCDOA/AT | - Ongoing |  |  |  |
| 7.2.2e. Handy Helpers volunteer home maintenance team is expanded to serve more older adults. | OCDOA / VC55+ | - Paused at the start of COVID. Regrouped and transition services. Active again starting on Sept 1. - Hope Renovations completing inside repairs using strict PPE guidelines - Housing department provided funding. - Handy Helpers completing outside repairs - CARES Act helping to pay. And received additional funding from the Sheriff’s Office which will allow additional ramps to be completed. - Sheriff’s Offices offering staff assistance for the HH volunteers during the implementation phase of the ramps - Hand Helper volunteers have completed 3 ramps since returning. We've also partnered with Hope Renovations on 3 homes for grab bars or indoor stair railings. - Can refer on OCDOA website or call aging helpline at 919 968 2087 |  |  |  |
| Strategy 7.2.3: Emergency preparedness education reflects and incorporates the needs of older adults. |  |  |  |  |  |
| 7.2.3a. Emergency Preparedness Checklist is revised to reflect senior issues. | ES, Health Dept, Sherff’s Dept, Town Police Depts, CEF | - Checklist was completed. - Distributing widely, esp with hurricane season. COVID impacts ability to shelter folks during emergencies - Aging Transitions team has made this a mandatory document in all new client files and will retroactively complete with all existing clients |  |  |  |
| Objective 7.3: Improve collaboration between medical providers and OCDOA. |  |  |  |  |  |
| Strategy 7.3.1: Develop collaborative projects between OCDOA and healthcare providers. |  |  |  |  |  |
| 7.3.1a. At least one collaborative project is created between the OCDOA and UNC Health Care (Senior Alliance), focused on assembling an inventory of social services available to seniors in a centralized database. | OCDOA/AT and UNC Health Care (Senior Alliance) | - NC Cares 360 launched in late June - long term goal is to communicate directly with community organizations, especially regarding referrals - UNC Health Care is ramping up screening for social determinants of health, especially around food insecurity. |  |  |  |
| 7.3.1b. At least one collaborative project is created between the OCDOA and Piedmont Health. | OCDOA, Piedmont Health | - OCDOA plans to work with Piedmont and AuthoraCare on collaborative projects this year. |  |  |  |
| Objective 7.4: Address the problem of food insecurity among older adults. |  |  |  |  |  |
| Strategy 7.4.1: Increase capacity to provide more home-delivered meals and groceries to older adults, especially those in rural areas. |  |  |  |  |  |
| 7.4.1a. More volunteers are recruited and trained to assist with meal preparation and/or meal delivery. | Chapel Hill-Carrboro Meals on Wheels, OCIM, Orange County Rural Alliance (OCRA), OCDOA, DEAPR | - Family First Funds received during COVID to expand Meals on Wheels programs - Due to COVID, MOW are using fewer volunteers now as we switched from daily hot meal delivery in the southern part of the county to once per week delivery of a frozen food box (containing five complete meals) and a bag of fresh fruit. Fewer volunteers also in the North as routes usually done by two people are done by one (no pairing in cars). - Due to COVID we did start a volunteer phone brigade that calls recipients every other weekday since we cannot do our daily check-in at delivery. - UNC PiAP funds supported buying butter, milk, and eggs from Latta's Eggs and Mapleview Farms. UNC students working with OCRA to deliver food weekly to 41 rural seniors in need during COVID - OCDOA continues offering grocery and medication delivery |  |  |  |
| 7.4.1b Collaboration between county agencies to create a uniform meal intake application | OCDOA, DSS, CHCMOW, OCRA, OCIM | - On June 29, CHCMOW and OCRA officially merged to become Meals on Wheels Orange County, NC. - Planning a meeting to start discussion around application |  |  |  |
| 7.4.1c. New drop-off and pick up points for meal delivery volunteers are established in rural areas. | Chapel Hill-Carrboro Meals on Wheels, OCIM, Orange County Rural Alliance (OCRA), OCDOA, DEAPR | (see 7.4.1a and 7.4.3a.) |  |  |  |
| 7.4.1f. Quarterly meetings between relevant organizations are established to discuss eligibility criteria and geographic coverage for each organization and to increase coordination. | Chapel Hill-Carrboro Meals on Wheels (MOW), OCIM, Orange County Rural Alliance (OCRA), OCDOA | (see 7.4.1a and 7.4.3a.) |  |  |  |
| Strategy 7.4.2: Improve representation for older adults on food and nutrition-related community organizations. |  |  |  |  |  |
| 7.4.2a. Person advocating for the needs of older adults is represented on the Orange County Food Council. | OCDOA/ Advisory Board | Board has paused, revisit later |  |  |  |
| Strategy 7.4.3: Increase awareness of food services for older adults. |  |  |  |  |  |
| 7.4.3a. Increased participation in programs like SNAP, Commodity Supplemental Food Program, and Meals on Wheels. | OCDOA, DSS IFC OCIM, OCRA | - DSS actively enrolling in SNAP - OCDOA Commodity food boxes: ~ 300 participants, no cap on enrollment (income requirements), phone application, distribution at 5 sites across the county, law enforcement has helped deliver boxes, someone else can pick up for you. - At the start of COVID, OCDOA transitioned to a 3 days/wk curbside lunch program. Currently at over 1000 meals/wk. Law enforcement is helping deliver meals to transit dependent seniors. - OCDOA received additional CARES funding which was routed through AAA to go to MOW OC NC. - Related to merger and the pandemic, MOW overall service numbers and areas increased. We now serve approximately b/t 1100-1200 meals per week (OCRA recipients during pandemic moved from 2 meals per week to 5), and also includes distribution of emergency food and supply boxes to recipients most in need who no longer have access or ability to purchase additional food and supplies beyond what MOW regularly delivers. MOW has also been supplying (when needed) in regular deliveries - toilet paper, paper towels. masks, hand sanitizer, ensure. |  |  |  |
| Objective 7.5: Promote and support the growth of the "Village"/neighborhood model of community support across all of Orange County for individuals aging in their homes. |  |  |  |  |  |
| Strategy 7.5.1: Increase the number and variety of “village” model programs/neighborhoods. |  |  |  |  |  |
| 7.5.1a. Increased number of village groups in Orange County. | OCDOA | - Team including the Jackson Center, UNC PiAP, and Charles House are exploring neighborhood elder care model in Northside. Focusing on building up current structures and learning more about residents this year. - Neighborhood connections SRT ongoing, but much of their work is on hold due to COVID - Neighborhood Connections Resource Guide available online |  |  |  |
| 7.5.1c. “Care navigator” programs are created by village groups to assist members with aging in place needs and connect residents to OCDOA. | OCDOA | On hold due to COVID |  |  |  |
| Objective 7.6: Support planning for and fulfillment of individual goals in all stages at the end of life. |  |  |  |  |  |
| Strategy 7.6.1: Build awareness about end of life planning by increasing visibility of end of life issues, normalizing end of life conversations, and supporting educational initiatives for community members. |  |  |  |  |  |
| 7.6.1a. End of Life awareness campaign is created, including dissemination of end of life planning materials and promotion of end of life planning conversations. | OCDOA, in collaboration with the UNC Partnerships in Aging Program, UNC Health Care, Orange County Health Department, OCIM, and IFC | - AuthoraCare hosting virtual workshops and webinars about decision making and diversity at EOL, and providing individual counseling - OCDOA continues to share document created related to COVID emergency and serious illness plan, to help implementing advanced directives (https://www.orangecountync.gov/DocumentCenter/View/10503) |  |  |  |
| 7.6.1b. Health Care Decisions Day and/or Advance Care Planning Awareness month are recognized and promoted. | OCDOA, in collaboration with the UNC Partnerships in Aging Program, UNC Health Care, Orange County Health Department, OCIM, and IFC | - Planned April 15th events were canceled due to COVID. Many groups still shared relevant materials through communication channels such as e-newsletters. |  |  |  |
| 7.6.1c. Information and ongoing educational opportunities about end of life issues are offered through OCDOA (e.g., webpage, seminars, speakers, and written materials). | OCDOA, in collaboration with the UNC Partnerships in Aging Program, UNC Health Care, Orange County Health Department, OCIM, and IFC | - OCDOA EOL SRT hosting virtual event “Voluntary Stopping of Eating and Drinking: A Little Known EOL Option” on Sep 22 - Advanced Care Planning education provided for CG support group | - OCDOA EOL SRT hosting virtual event “End of Life Autonomy: Making Choices that are Right for You” on Oct 14 - OCDOA EOL SRT hosting virtual event “EOL Care Planning Event” re: The Conversation Project on Nov 16 (discussing Dying Right NC new SAD form on website) |  |  |
| 7.6.1d. Five Wishes and other documents are available for Orange County residents at multiple locations (e.g., senior centers, libraries, major healthcare systems) and in various languages. | OCDOA, in collaboration with the UNC Partnerships in Aging Program, UNC Health Care, Orange County Health Department, OCIM, and IFC | - Still available |  |  |  |
| 7.6.1e. More people are aware of and are using OCDOA notary services. | OCDOA, in collaboration with the UNC Partnerships in Aging Program, UNC Health Care, Orange County Health Department, OCIM, and IFC | - Free Notary services at OCDOA are advertised in the Senior Times - By appointment |  |  |  |
| 7.6.1f. Connections with diverse community partners, including schools, faith-based organizations, long- term care facilities, etc., are created to promote end of life discussions. | OCDOA, in collaboration with the UNC Partnerships in Aging Program, UNC Health Care, Orange County Health Department, OCIM, and IFC | - LTC SRT regrouping after a pause due to COVID. (see 3.5.1a for more details) |  |  |  |
| 7.6.1g. Volunteer legal service is made available twice yearly to assist older adults in writing/changing wills and other legal documents (e.g., power of attorney, living will). | OCDOA, in collaboration with the UNC Partnerships in Aging Program, UNC Health Care, Orange County Health Department, OCIM, and IFC | - Free Legal Aid Services at OCDOA for low-income seniors are advertised in the Senior Times - By appointment |  |  |  |
| Strategy 7.6.2: Reduce provider-side barriers to access and use of completed Advanced Care Planning forms when needed and support provider education. |  |  |  |  |  |
| 7.6.2a. Local healthcare systems incorporate Advanced Care directives in Electronic Medical Records and actively educate providers on how to use/access. | UNC Health Care, Duke Health, UNC Allied Health, Piedmont Health, UNC Partnerships in Aging Program, EMS |  |  |  |  |
| 7.6.2b. Healthcare providers incorporate end-of-life discussions into routine care, and provide/complete Medical Orders for Scope of Treatment (MOST) and Do Not Resuscitate (DNR) forms for their patients as appropriate. | UNC Health Care, Duke Health, UNC Allied Health, Piedmont Health, UNC Partnerships in Aging Program, EMS | - At start of COVID, Piedmont Health reviewed advanced directives, especially with folks in LTC, and are checking in at 3-month periods. |  |  |  |
| 7.6.2c. EMS task force on mobile MOST/DNR forms recommends ways to authorize MOST/DNR care wishes when away from home. | UNC Health Care, Duke Health, UNC Allied Health, Piedmont Health, UNC Partnerships in Aging Program, EMS | - NHs have been a large source of contact with people who are COVID positive. Clear communication of MOST/DNR wishes are especially important during this time to assure that wishes are respected and to minimize unnecessary exposure. - EMS is reaching out to primary health care providers to share information regarding bracelets. The next steps are to do a press release. - EMS shared flyer about DNRs and bracelets with Workgroup to help spread the word. OCDOA is distributing flyer during lunch and food box distributions. - Aging Transitions will be trained by EMS to enroll community members and distribute bracelets |  |  |  |
| 7.6.2d. UNC promotes professional training on end of life issues and palliative medicine in curriculum, and continuing education opportunities. | UNC Health Care, Duke Health, UNC Allied Health, Piedmont Health, UNC Partnerships in Aging Program, EMS | - UNC PiAP and Interprofessional Education program included EOL components in course - (see 7.2.1 for more updates on UNC Hillsborough Hospital work) |  |  |  |
| Strategy 7.6.3: Support legislation and policy change to facilitate end of life planning and increase choice. |  |  |  |  |  |
| 7.6.3b. Legislation is supported to increase choice at end of life. | Orange County Advisory Board on Aging, with support from Towns of Chapel Hill, Carrboro and Hillsborough, Orange County Health Department | Will request updates on plans for HB 879: Dying Right NC legislation that was previously proposed |  |  |  |
| 7.6.3c. Green burial options are expanded. | Orange County Advisory Board on Aging, with support from Towns of Chapel Hill, Carrboro and Hillsborough | No updates at this time |  |  |  |
| Objective 6.4: Expand enriching volunteer opportunities for older adults. |  |  |  |  |  |
| Strategy 6.4.1: Create and expand substantive, skills-based, and intergenerational volunteer opportunities for older adults. |  |  |  |  |  |
| 6.4.1a. Older adults are matched to volunteer opportunities based on skills and interests. | OCDOA / VC55+ | - Intake has moved to a virtual format. Most in-person opportunities are on hold due to COVID. Volunteers have been focusing on non-contact services like Telephone Reassurance and Friend to Friend. Handy Helpers is up and running (new safety protocols in place) |  |  |  |
| 6.4.1b. Older adult volunteers report feeling satisfied and supported in their volunteer roles. | OCDOA / VC55+ | - Survey results (averages from two surveys from last year covering 1st and 2nd six months). On average: - Sent to 507 volunteers. 282 volunteers responded. - 233 people (86.94%) reported that volunteering with the VC55+ has positively affected their mental well-being; 23 people (8.58%) reported they were not sure; 12 people (4.48%) reported it has not - 121 people (45.83%) reported that volunteering with VC55+ has positively affected their physical well-being; 67 people (25.38%) reported they were not sure; 76 people (28.79%) reported it has not - 216 people (76.60%) reported that they have made new social connections through volunteering with VC55+; 52 people reported (18.44%) no new social connections; 14 (4.96%) reported that they were “not sure.” - Of those who reported new social connections, 159 people (76.81%) reported they’ve made three or more social connections, 29 people (14.01%) report they’ve made 2 or more social connections, and 19 (9.18%) report they’ve made one new social connection. |  |  |  |
| 6.4.1c. Older adult seeking volunteer opportunities outside of OCDOA are referred to appropriate organizations, such as Hands on Triangle. | OCDOA / VC55+ | - Ongoing as needed |  |  |  |
| 6.4.1d. More people are educated through Project EngAGE to become volunteer leaders and develop senior resource team projects. | OCDOA / VC55+ | - Policy and Advocacy SRT hosted virtual presentation regarding Voting Safely in the 2020 Election on Aug 13 | - IG SRT and local law enforcement are hosting Story Time Adventure event, to be viewed from cars on Nov 7 |  |  |
| Strategy 6.4.2: Plan and implement community-based volunteer programs that support persons to age in community. |  |  |  |  |  |
| 6.4.2a: Existing community-based volunteer programs around aging in community are sustained and expanded (i.e., Handy Helpers, Volunteer Drivers, Friend to Friend, SALT). | OCDOA / VC55+ | - OCDOA has adapted their community programs. For example, they expanded Telephone Reassurance Volunteers, transitioned Friend2Friend to a phone-based partnership and expanded, and created lunch and grocery delivery volunteer programs (see 6.4.1a for additional details). Renewed attention to planning for sustainability of Handy Helpers program |  |  |  |
| 6.4.2b: New community-based volunteer programs are planned and implemented that address social isolation and support persons to age in community. | OCDOA / VC55+ | - (see 6.4.1a) |  |  |  |
| Objective 5.1: Ensure a welcoming, inclusive, and livable community. |  |  |  |  |  |
| Strategy 5.1.3: Continue and expand efforts to make Orange County a dementia-capable community. |  |  |  |  |  |
| 5.1.3a. Funding is secured to continue work of Administration for Community Living Dementia Capable Community grant, which ends September 2018. | OCDOA | - Dementia friendly business trainings provided virtually. Congregate senior apartments were able to train folks across the triangle since it was virtual |  |  |  |
| 5.1.3b. More people are aware of and attend the Dementia 101 trainings, Memory Cafés, and Memory Cafés on the Move. | OCDOA | - Holding fewer formal dementia chats and maintaining Memory Cafes in virtual format |  |  |  |
| 5.1.3c. An on-going volunteer group for recruiting businesses and providing Dementia Friendly Business training is created. | OCDOA | - Ongoing (see 7.2.1 for details on UNC Hillsborough Hospitals related work) |  |  |  |
| 5.1.3d. More caregivers are referred to and served each year by the OCDOA. | OCDOA | - Ongoing (Aging helpline being distributed widely) |  |  |  |
| 5.1.3e. Strategies and supports are developed for individuals living alone with dementia. | OCDOA/AT, DSS | - Ongoing |  |  |  |
| Objective 3.5: Activate the community to support and improve quality of life for older adults living in long-term care settings. |  |  |  |  |  |
| Strategy 3.5.1: Engage community volunteers in long-term care facilities and home care services. |  |  |  |  |  |
| 3.5.1a: Vc55+ to provide volunteer opportunities for people interested in enriching the lives of persons receiving long-term care services | VC55+ | - LTC SRT regrouping after a pause due to COVID. Creating round table discussions for ALF and adult day facilities and another one for SNFs. Starting with management but hoping to include direct care (e.g. CNAs) down the line. Will meet once a month. First meeting to establish the structure of the round table groups will be on October 8th 1pm. Contact Shenae for meeting link. |  |  |  |
| 3.5.1b: Opportunities are created for long-term care residents to get out into the community, with help of volunteers | VC55+ | - On hold during this time |  |  |  |
| 3.5.1c: Nursing Home and Adult Care Home Advisory Committee members promote activities that support resident and staff well-being and that reduce social isolation | Community Advisory Committee (CAC) members, Ombudsman | - On hold during this time |  |  |  |

Communication and Information: All Workgroup + OCDOA Communication Dept. – Year 4 Priorities

| Indicator | Lead Agency | Q1: Jul – Sep 2020 Activities | Q2: Oct – Dec 2020 Activities | Q3: Jan – Mar 2021 Activities | Q4: Apr – Jun 2021 Activities |
| --- | --- | --- | --- | --- | --- |
| Objective 8.1: Increase the accessibility of information regarding available programs, services, and resources. |  |  |  |  |  |
| Strategy 8.1.1: Identify liaisons within medical offices, faith-based organizations, civic and community organizations, libraries, etc. to post/distribute OCDOA information. |  |  |  |  |  |
| 8.1.1a. Comprehensive list of liaisons is created and maintained. |  | UNC Partnerships in Aging Program (PiAP) created an online calendar of events and is now sharing our “Special Events” on their website: http://partnershipsinaging.unc.edu/ |  |  |  |
| 8.1.1b. Information sharing is facilitated by liaisons within their organizations. | OCDOA, SHIIP, VC 55+ | Fliers continue to be a main method of distributing information through the Senior Centers with lunch program, food box distributions, Piedmont, Town of CH, and DSS |  |  |  |
| 8.1.1c. Information is distributed at least quarterly to designated liaisons. |  | - Ongoing - See 7.2.2b. regarding Faith Outreach Qrtly Breakfast |  |  |  |
| 8.1.1d. Liaisons are created with non-English organizations. | OCDOA, El Centro NC | Maintaining established relationships. Information is shared both ways. |  |  |  |
| 8.1.1e. Liaisons are created with neighborhood groups. |  | Continue to share information and respond to neighborhood group comments and inquiries |  |  |  |
| Strategy 8.1.2: Make OCDOA communications available in a variety of languages. |  |  |  |  |  |
| 8.1.2a. Communications are sent out to non-English media sources and posted at relevant locations and community agencies. | OCDOA, Orange County Government – Community Relations | Ongoing |  |  |  |
| Strategy 8.1.3: Improve the Senior Times to be more readable and user-friendly. |  |  |  |  |  |
| 8.1.3a. Print versions of the Senior Times are in larger print and with less information. | OCDOA | - Submitted program improvement request to CivicPlus to improve the functionality of our online WebTrac calendar - Sr. Times (ST) Improvement Workgroup meet weekly to improve organization, readability and look of the ST - Working with County graphic designer to implement Workgroup’s recommendations - Some ST Workgroup recommendations have already been implemented in the Fall 2020 ST - Preliminary work has begun on creating a ST submission template and database - ST programmer training planning underway to train programmers to use new ST submission template/database and guidelines |  |  |  |
| 8.1.3b. Additional versions of the Senior Times are explored, including print and online versions in Spanish and Mandarin (and other languages as needed) and an audible version. |  |  |  |  |  |
| 8.1.3c. Drop off locations are expanded. |  |  |  |  |  |
| Strategy 8.1.4: Expand capacity for electronic/digital information dissemination. |  |  |  |  |  |
| 8.1.4a. OCDOA webpage hits increased each year. | OCDOA | Total page views (hits): Top five pages: Information pending |  |  |  |
| 8.1.4b. OCDOA Facebook page has more friends/hits each year. | OCDOA | Total Facebook “Likes” 583. Up 1.22% from previous quarter |  |  |  |
| 8.1.4c. Number of Listserv members increased each year. | OCDOA – Endless Possibilities, Community News for Caregivers | - Endless Possibilities: 3477 subscribers - Community News for Caregivers: 679 subscribers |  |  |  |
| 8.1.4d. New methods established to keep up with technological advances. | OCDOA, OC IT, OC Community Relations | - RecTrac Projects waiting until upgrades are initiated and completed - RecTrac Power User Group was created and met, deciding to upgrade RecTrac in the Winter 2021 - Launched new OCDOA YouTube channel https://www.youtube.com/channel/UCEEl8ytoBeTy1qB0YGl_0mQ?view_as=subscriber |  |  |  |
| 8.1.4e. People report they are hearing about events/programming through these sources when they register. |  | Ongoing |  |  |  |
| Strategy 8.1.5: Continue to use media sources that do not rely on electronic sources. |  |  |  |  |  |
| 8.1.5a. Local radio stations, television stations, and newspapers are used to advertise OCDOA events/programming. | OCDOA, OC – Community Relations | - July 10, UNC Trauma Talk podcast: Making Seniors Homes Safer: Staying Safe While Social Distancing - Sept. 18, WHUP interview with VC 55+ Project EngAGE: End of Life VSED - Sept. 23, Aging Matters Radio Show interview with OCDOA Wellness & Communications staff: How to Stay Healthy During COVID and Beyond |  |  |  |
| 8.1.5b. OCDOA program, service, and resource information is distributed at community events. | OCDOA, Transitions Guiding Lights NC, El Centro NC, UNC Health Care – Benefits, Orange County Schools, Cedar Grove Community Center | - All in person community events were canceled in response to the COVID-19 pandemic. |  |  |  |
| 8.1.5c. Information “Toolkits” are created that volunteers can use to share OCDOA program and service information with others. |  | - Welcome packet has been put on hold due to COVID and until we determine what our new “normal” will look like at the centers when we return |  |  |  |
| 8.1.5d. The number of Project EngAGE graduates is increased each year. |  |  |  |  |  |
| 8.1.5e. People report they are hearing about events/programming through these sources when they register. |  |  |  |  |  |
| Strategy 8.1.6: Partner with other organizations to promote and publicize each other’s events and information. |  |  |  |  |  |
| 8.1.6a. Community groups, organizations, and key liaisons are identified. | OCDOA, SHIIP, VC 55+, Transitions Guiding Lights NC, El Centro NC, UNC Health Care – Benefits, Orange County Schools, Cedar Grove Community Center | - OCDOA Transportation Specialist continues to attend monthly/quarterly meetings at CHT and OCPT. As well as, Healthy Carolinians of Orange County – Access to Care Committee and NC Senior Driver Safety Coalition - OCDOA Transportation Specialist had an introductory meeting with Stroke Support Group facilitator at UNC Health - OC Housing Preservation Coalition has developed a website (www.orangecountync.gov/ochpc) and has begun conversations with UNC Health to make more direct referrals from their org to OCHPC. - Also see 8.1.1b; 8.1.5b |  |  |  |
| 8.1.6b. Events are publicized by multiple organizations. | OCDOA, SHIIP, VC 55+, Transitions Guiding Lights NC, El Centro NC, UNC Health Care – Benefits, Orange County Schools, Cedar Grove Community Center | - Publicizing Webinars and Virtual Events via Endless Possibilities electronic newsletter, while in person Events are on hold due to COVID - Employment related events publicized to OC Library patrons - Also see 8.1.1b |  |  |  |
| 8.1.6c. Senior center events/programming is advertised in community center newsletters, calendars, and on-site. |  | - Community Center advertising on hold due to COVID closures - Continue to advertise events at Senior Centers through Senior Times, Flyers, Newsletters and listservs |  |  |  |
| 8.1.6d. Community center events are posted at senior centers and included in listserv mailings. | OCDOA, Efland-Cheeks Community Center, Rogers Road Community Center, Cedar Grove Community Center | - Most in person events on hold due to COVID restrictions |  |  |  |
| 8.1.6e. A link to program information is established on DEAPR’s website, and vice versa. |  | No longer relevant |  |  |  |
| Strategy 8.1.7: Collect data on how people prefer to be communicated with and/or how they find out about events. |  |  |  |  |  |
| 8.1.7a. People are asked about how they found out about events/programming upon registration, and that data is utilized in communication plan. |  | Ongoing, completed during registration process (see 8.1.4e) |  |  |  |